## Output Summary
| Transmitted by the GRB Chair |  | GRB subjects for the future: Results of the informal meetings |  |  |  |  | Informal document GRB-64-08 (64th GRB, 5-7 September 2016, agenda item 16)
This file is an update of informal document GRE-62-08-Rev.2 amended at a meeting in Brussels on 4-5 July 2016
No | Existing regulation (n°), New regulation (GTR, UN, RE3, SR1) | Topic | Explanations | Short, Mid or Long terms | When to start | When to close | Constracting parties and/or organization concern | Discussions in GRB, IWG, Task force | Priority | Comments
| R51-03 | Limit value | Evaluation of limit values of phase 3 | M | 2018 | 2020 | EC, Japan, OICA, France, UK, NL |  | B | Préparation of the work in 2018: how to do ? For EC: in the context of Article 11 of Regulation (EU) 540/2014, for the EC study on sound level limits, that should be published by 1/7/2021
| R51-03 | Annexe 3 - Update technical progress | Improvement of the test method for M3 gasoline vehicles, Non lockable gear for Passenger car, Hybrid vehicle | S | 2016 |  | EC, Japan, France, OICA, UK | GRB discussions with ISO imput | A
| R51-03 | Next-generation test methods | The current test methods take a great number of man-hours and a long time; next-generation test methods need to be studied. | M | 2016 | 2020 | Japan, OICA, France, UK |  | B | to be managed with phase 3
:l | R51-03 | ASEP | ASEP Work package : 1) update the text to improve clarity and simplification in short term 2) Missing sound limit values for N1 and Offroad in Annex7 para. 5.3 to be added. 3) Series hybrid vehicles are excluded from the ASEP until 30 June 2019; new test methods will be necessary in R51. 4) ASEP as a part of type approval (not as a manufacturer declaration) 5) More general technical review in cooperation with ISO (Improvement of methods) |  | 2016 | 2019 |  | IWG suggested | A | not only for R51-03, but also for R41-04
| R51-03 | gtr on pass‐by test procedure | As agreed in grb in 2002 (?), it should be considered to develop a gtr after finalization of R51.03 | L | 2018 |  | OICA, France, UK |  | B
| R51-03, R41-04, R9 and R63 | Pass by test light for roadside-checks and PTI | Because stationary noise has often lost the direct link of sound of vehicles in motion (e.g. mapping, variable geometries, gear sensors, OBD modifications, etc.) or when stationnary noise test is not applicable (HEV) . The test should be performed easily at usual streets without buildings and walls and the result (OK or not OK) should consider differences in measurement and surface etc. (tolerances of speed, rpm, ageing of silencer/vehicle, etc.). It may be a longterm substitute to stationary sound | M | 2016 | 2020 | Germany, Japan, OICA, France, UK, NL,IMMA | To be define | A for L cat To be define for M &N category | Work in progress for L cat Clarification have to be done about scope, national regulation, responsabilities, …
| R51-03 or RE3 | Special Purpose Vehicles | SPV like mobile cranes etc are not covered by UNECE (see Framework Directive 2007/46) | S | 2016 | ASAP | OICA, France, UK | GRB | A
| All vehicle regulation | Indoor type approval | Include indoor testing as an alternative to outdoor test tracks as test facility to noise tests | S / M | 2017 | 2018 -2019 (ECE51) | OICA, France, EC | GRB work with ISO | A
| All | Virtual Type Approval | Some Regulations enable an assessment of compliance by calculation, instead of physical testing. GRB should start considering to develop the framework for type approval based on calculation | L |  |  | OICA, France |  | B
| R9, R63, R92 | Anti-Tampering, other requirements | Information / exchange of views on the probable tabling of proposals to GRB and the estimated time schedule; | S | 2016 | 2017 | EC, IMMA, Germany, Japan |  |  | To be include in line 9
| R41-04, R9, R63, R92 | Limit value | The strengthening of the limit values as proposed by the European Commission will be considered. | S | 2016 |  | EC |  | A | - Review of R9 and R63 limit values not a priority for Japan. - EC forsees a strengthening of limit values for category L as outlined in the EU regulation. - IMMA and some CP's consider such exercise not useful until in use compliance problems are solved. Strengthening of type approval limit values would not solve concerns of citizens, which is caused by aftermarket (e.g. illegal or tampered mufflers); It would even give a negative effect: Even more riders will replace/tamper their original muffler. EC comment: EU type-approval legislation concerns new vehicles and therefore includes sound level limits for such vehicles, as decided through the co-decision process.
| R41-04 | Update technical progress | Collecting information on experience with R41.04, that could lead to proposals for improvement : Clarification of the ASEP for motorcycles (CVT), hybrid electric vehicles | S |  | 2018-2019 | Japan, IMMA |  | B
| R28 | "Pedestrian" horn | Much quieter than present situation (eg rgulation 3/2014/EC part 1 §1.3 and part 2 §1,5) Horn related to vehicle speed | S | 2016 | On going | Germany, France, India | IWG ? | B
| R28 | Update technical progress | Revision of regulation | S | 2016 | On going | Russian federation, IMMA, OICA, France | IWG ? | A
| R28 | Horn (bell) | EC L1A category tests Harmonize L1A AWD specification | S / M | 2016 | On going | France | IWG ? | B
| R28 or RE3 or new regulation | Reversing signal | Reversing alarm of M &N category vehicles because present situation causes a lot of negative reactions from peoples living in urban-areas (alarm belongs to road-building vehicles with road-building backround noise), to include additionnal active safety | M | 2016 |  | Germany, Hungaria, France, OICA | GRB | A to be confirm by GRB
| R117-03 | Tyre noise limits related to ECE51.03 | General discussion about the application of R117 in junction with OEM tyres Alternative Test Conditions (50 km/h cruising / acceleration) | M | 2016 |  | OICA | GRB | B
| R117-03 | Tyre noise limits | NL proposal to amend R 117 with stage 3 limits | S | 2015 | 2017-2018 | NL
| R117-03 | Tyre noise limits /retreaded tyres | - The scope of R117 may need to be extended with retreaded tyres (ref GRBinf doc 42-7). Or a separate regulation may be considered. Bipaver is studying a technical framework for the combination of different carcasses and tread profiles. | M |  |  | NL
| R117-03 (related to studless) | Clarification / addition of requirements | Addition of ice performance requirements for winter tyres | M |  | 2020 | Japan | GRRF &GRB | B
| QRTV (UN) | Non‐acoustic measures and update of technical progress | QRTV Work package : 1) Non‐acoustic measures : The new ECE Reg should be forwarded to other GRs for further development of alternative, non‐acoustic measures according to the footnote of the scope of Regulation. 2) Update technical progress : Review more recent studies on EVs to verify the effectiveness of ECE Rxxx QRTV |  | 2016 | 2017 | OICA, JAPAN, France | other GR's and IWG QRTV for UN | B
| QRTV (GTR) | Early establishment of QRTV-UNR and gtr | Harmonisation with the gtr to be developed in the future | On going | 2016 | On going | Japan, OICA |  | A related to US regulation publication
| RE3 or GTR | Interior Noise | ISO is undertaking a full review of the scope and technical issues related to ISO 5128 ‐ which is presently incorporated into RE3 | M |  | On going | OICA, Hungria, Russian Federation |  | B | report from ISO
|  | Sound emission by agricultural and forestry tractors | Sound emission by agricultural and forestry tractors, in view of the future update to technical progress of the new type approval. Opportunity to harmonize. | M |  | On going | EC, France |  | B
|  | Noise emitted by the engine cooling system |  | S / M |  | 2020 | Brazil,OICA |  | A related to Brazil
| All | Update on instrumentation | Sound level meter specifications (analyzer, last IEC) | S |  | On going | France |  | A
|  | Method for evaluating effectiveness of noise regulations | Exchange information on methods to measure traffic noise, and relating these to the impact of vehicle regulations. | L |  |  | IMMA |  | B
| - | Delivery noise | Harmonize testing method on delivery vehicle | M |  |  | France, NL |  |  | Report from NL expected sept 2016
| - | Quiet City Bus | Harmonize testing method for Quiet City Bus | M |  |  | OICA | ISO
| - | Siren | Harmonize testing method for siren To be include in RE3 or a new regulation | L |  |  | France |  | B
|  | Road noise | Method or recommandation for definition of the type of road surface regarding rolling noise. |  |  |  | Russian federation / EC / NL |  | B
| QRTV (UN/GTR) | Extension of the scope | Develop a definition for quiet vehicles (not just electrical or hybrid) and a qualification method for vehicles to be considered as quiet | M-L |  | 2020+ | Russian Federation looking for help of other CPs and OICA
|  | Infrasound | Assess the need for rulemaking as the first step. Information exchange. | M |  | 2018? | Russian Federation looking for help of other CPs
| All | Clarification of interpretation | Definition of representative vehicle, … | S | 2016 |  |  |  | A (A for ECE51.03)
| R117-03 | Indoor testing (on drum) | [5 empty] | ISO | B
| R117-03 | Alignment ECE117 and ISO 13325,2003 | [5 empty] | ISO | B
| R117-03 + ECE51 | Improve reproducibility | Track aligment and temperature correction | [5 empty] | B