## Slide 1: 70th GRBP 11-13 September 2019
Study on requirements and test procedures for TPMS for vehicle categories M2, M3, N2, N3, O3 and O4
Transmitted by the expert from EC
Informal document GRBP-70-14
(70th GRB, 11-13 September 2019,
agenda item 14)

## Slide 2: The political mandate for TPMS
Remit for the General Safety Regulation is set by the European Parliament’s legislative resolution of 16 April 2019: http://www.europarl.europa.eu/doceo/document/TA-8-2019-0391_EN.html
Required functionality:
  'tyre pressure monitoring system' means a system fitted on a vehicle which can evaluate the pressure of the tyres or the variation of pressure over time and transmit corresponding information to the user while the vehicle is running;
  The TPM system shall:
    Be capable of working with environmental conditions in all Member States
    Provide an appropriate warning to the driver
    Be designed to avoid resetting or recalibrating at a low tyre pressure

## Slide 3: Task and relevant timelines
TRL’s task is to:
  Draft requirements and test procedures for type-approval of Tyre Pressure Monitoring (TPM) Systems
  Trial the draft procedures
  To be based on physical test (e.g. test track-based) based on the procedure as defined by UN R141 under additional consideration of the proposals submitted by third parties
Implementation:
  Vehicle categories: M2, M3, N2, N3, O3, O4
  New types 05/2022, Existing types 05/2024 (actual dates defined relative to date of entry into force, currently assumed to be November 2019)

## Slide 4: Technical approach and delivery status
Bilateral meetings (OEMs, Tier 1 experts)
Review of standards, test procedures and research
Draft outline of regulation technical contents
EC review
Develop regulatory technical text
EC review
Trial test procedure and update
Report to EC
Status:
Completed
In progress
Started
Not started
Not started
Not started

## Slide 5: Timelines TRL TPMS workstream
Stakeholder consultation in parallel with development of requirements/testing plan: April 2020
Testing of draft method: April/May 2020
Interim report: June 2020
Review of interim report : during June/July 2020
Finalise work: November 2020

## Slide 6: Thank you for your attention DG GROW – Unit C4
Further information:
http://ec.europa.eu/growth/sectors/automotive/index_en.htm