| UNITED NATIONS ECONOMIC COMMISSION FOR EUROPE | WORLD HEALTH ORGANIZATION REGIONAL OFFICE FOR EUROPE |
| --- | --- |

MEETING OF THE PARTIES TO

THE PROTOCOL ON WATER AND HEALTH

TO THE CONVENTION ON THE PROTECTION

AND USE OF TRANSBOUNDARY

WATERCOURSES AND INTERNATIONAL LAKES

Task Force on Indicators and Reporting

First meeting

Geneva, 13–14 March 2008

Agenda item 9

PROPOSED steps and Timeframe for the achievement of the PROGRAMME OF WORK OF THE TASK FORCE ON INDICATORS AND REPORTING

- 13-14 March 2008 (Geneva): First meeting of the Task Force to discuss the first draft of the guidelines on target setting; a set of indicators for targets under article 6 of the Protocol (in particular targets under article 6, paragraphs 2 (f)–(n)); the workshop to share experience on target setting and future steps by the Task Force.

- April-September 2008: Preparation by the Core Group of a draft of the guidelines on target setting, evaluation and reporting, including a set of indicators, based on comments received by the Task Force (if needed drafting meeting of the Core Group will be organized within this period).

- 2-4 December 2008: Workshop on experience in target setting by Parties to the Protocol and second meeting of the Task Force on Indicators and Reporting. These meetings will allow finalizing the guidelines on target setting, evaluation and reporting. A first draft of the guidelines for summary reports will also be presented for comments.

- March 2009: Third meeting of the Task Force to approve final draft of the guidelines for target setting, evaluation and reporting and the guidelines for summary report as finalized by the Core Group, and to organize the reporting exercise for the second meeting of the Parties.

- April-August 2009: pilot reporting by countries (Parties, Signatories and other interested countries)

- September-December 2009: implementation report prepared by an independent expert on the basis of reports submitted by countries and terms of reference agreed by the Task Force, with the assistance of the Joint Secretariat and the Compliance Committee; including a round of comments by focal points and key stakeholders

- January 2010: presentation of the final draft of the guidelines on target setting and reporting; and of the  report on implementation and progress in the UNECE region to the Working Group on Water and Health

- February –May 2009: Finalization, editing, translation and printing of the report

- June 2010 (to be confirmed): presentation of the final draft of the guidelines on target setting and reporting; and of the report on implementation and progress in the UNECE region to the second meeting of the Parties.